## Gantt Chart Template
GANTT CHART LEAD THE WAY | [27 empty] | https://goo.gl/PXLbMe
| PROJECT TITLE | Lead the Way |  |  |  |  | COMPANY NAME
| PROJECT MANAGER | Derrick Thompson |  |  |  |  | DATE | [8 empty] | 2023-04-17
[7 empty] | PHASE ONE | [14 empty] | PHASE TWO | [14 empty] | PHASE THREE | [14 empty] | PHASE FOUR
WBS NUMBER | TASK TITLE | TASK OWNER | START DATE | DUE DATE | DURATION (DAYS) | PCT OF TASK COMPLETE | Augst 21st 2023 |  |  |  |  | August 28th 2023 |  |  |  |  | September 4th 2023 |  |  |  |  | September 11th 2023 |  |  |  |  | September 18th 2023 |  |  |  |  | September 25th 2023 |  |  |  |  | October 2nd 2023 |  |  |  |  | October 9th 2023 |  |  |  |  | October 16th 2023 |  |  |  |  | October 23rd 2023 |  |  |  |  | October 30th 2023 |  |  |  |  | November 6th
[7 empty] | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
1 | Ordering Robot Parts
1.1 | Research part suppliers | All | 2023-03-01 | 2023-04-25 | 54 | 100% | bar: Augst 21st 2023 M
1.2 | Create a list of parts to order | Jordan/Caihong | 2023-03-18 | 2023-04-25 | 37 | 50%
1.3 | Parts ordered | Sam B | 2023-04-21 | 2023-08-25 | 124 | 0%
1.3.1 | Parts are received | Sam B | 2023-08-25 | 2023-09-04 | 9 | 0%
1.4 | Inspect parts | Derrick T | 2023-08-25 | 2023-09-04 | 9 | 0%
1.5 | Assemble Parts | Sam B | 2023-09-04 | 2023-09-08 | 4 | 0%
1.6 | Document parts in inventory | Niko | 2023-09-04 | 2023-09-08 | 4 | 0%
2 | Designing model/prototype
2.1 | Create a working blueprint | Jordan/Sam | 2023-09-11 | 2023-09-15 | 4 | 0%
2.2 | Build prototype | Jordan/Sam | 2023-09-15 | 2023-09-22 | 7 | 0%
2.3 | Conduct user testing | Caihong | 2023-09-20 | 2023-09-27 | 7 | 0%
3 | All Hardware components are integrated together
3.1 | Soldering on Microcontroller | Sam B | 2023-09-29 | 2023-09-29 | 0 | 0%
3.2 | Develop proper power supply system | Sam B | 2023-10-02 | 2023-10-06 | 4 | 0%
3.2.1 | Battery Management | Niko | 2023-10-06 | 2023-10-11 | 5 | 0%
3.2.2 | Stress testing all hardware components | Caihong | 2023-10-16 | 2023-10-16 | 0 | 0%
3.3 | Conduct integration tests (everything works together) | Caihong | 2023-10-16 | 2023-10-20 | 4 | 0%
3.3.1 | Refine hardware system | Jordan | 2023-10-20 | 2023-10-25 | 5 | 0%
4 | The software allows the robot to follow the user
4.1 | Define software architecture | Derrick/Niko | 2023-10-23 | 2023-10-27 | 4 | 0%
4.2 | Develop infared/ultrasonic software | Derrick T | 2023-10-27 | 2023-10-31 | 4 | 0%
4.3 | Develop motion tracking algorithm | All | 2023-10-23 | 2023-11-10 | 17 | 0%
4.4 | Develop app/app functionality | Caihong | 2023-10-23 | 2023-11-06 | 13
4.5 | Develop camera facial recgonizition using robot kit template | Jordan | 2023-10-23 | 2023-11-06 | 13
4.6 | Test coverage and analysis | All | 2023-11-01 | 2023-11-10 | 9 | 0%

## Try Smartsheet
Try Smartsheet for Free